## Tabelle1
Activity number | Activity description | Partners | Original completion month | (Adjusted) Completion month | Work-package | Task | Comments
A1.1.1 | UdS will produce at least 3 reproducible SiV, and at least 3 reproducible GeV, centres in bulk diamonds (i.e. at least 6 diamonds in total) by ion implantation with an ion implanter. These will be used as single‑photon emitters in A1.1.3 at centre wavelengths of 738 nm and 602 nm, respectively, both with a bandwidth of < 2 nm. | UdS | 12 | 21 | 1 | 1.1 | Completed. February 2020 (M21). | 1 | 2018-06-01
A1.1.2 | Using the SiV and GeV implanted bulk diamonds from A1.1.1, UdS will investigate co‑doping with other ions (e.g. nitrogen, oxygen) to stabilise the SiV and GeV charge states in the bulk diamonds. UdS, in collaboration with PTB and FAU, will also investigate the brightness (i.e. the number of photons), single‑photon purity (g(2)(t=0)) and spectral characteristics (e.g. number of photons per wavelength) of individual SiV and GeV centres. | UdS, PTB, FAU | 12 | 21 | 1 | 1.1 | Completed. February 2020 (M21). | 2 | 2018-07-01
A1.1.3 | Using the bulk diamonds from A1.1.1 ‑ A1.1.2, UdS, in collaboration with FAU, will produce at least 5 thin diamond membranes (100 nm – 300 nm thickness) to be used for developing planar directional antennas in A1.1.4. Membranes with a thickness of 100 nm – 300 nm will be fabricated by a dry etch process. The required development steps will be: the development of an etch mask, the development of an etch process (RIE, ICP-RIE) to reach the target thickness, and the development of a break-out process to single out the individual membranes. | UdS, FAU | 18 | 28 | 1 | 1.1 | A1.1.3 will be delayed by 10 4 months to September March 2020 (M28M22). | 3 | 2018-08-01
A1.1.4 | UdS, in collaboration with FAU and PTB, will design and produce at least 3 different planar antenna structures using the thin diamond membranes produced in A1.1.3. The use of planar antenna structures will enable the SiV‑ and GeV‑centres to achieve extraction efficiencies, larger than 60 %, into standard air objectives with NA=0.8. (NB the collection efficiency will be determined in A1.1.9.) | UdS, FAU, PTB | 18 | 28 | 1 | 1.1 | A1.1.4 will be delayed by 10 4 months to September March 2020 (M28M22). | 4 | 2018-09-01
A1.1.5 | UdS will investigate the brightness (i.e. the number of photons), single photon purity (g(2)(0)) and spectral characteristics (e.g. number of photons per wavelength) of individual SiV‑ and GeV‑centres in the planar antenna structures developed in A1.1.4. The data from this activity will be compared with that from A1.1.2 in order to quantify the antenna enhancement of the detected single photon emission rate. | UdS | 24 | 30 | 1 | 1.1 | A1.1.5 will be delayed by to September March 2020 (M30M22) | 5 | 2018-10-01
A1.1.6 | PTB will develop and characterise a complete standard single‑photon source that will comprise a SiV centre in bulk diamond with and without a planar antenna structure provided by UdS and FAU (A1.1.2 and A1.1.4). The optical excitation scheme developed in A1.1.10 will be used for the excitation. The complete source will be characterised by PTB in terms of its photon flux, its single photon purity (g(2)(0)‑value), its spectral characteristics (e.g. number of photons per wavelength) and its stability using reference standards (i.e. calibrated spectrometers and calibrated photodetectors) that are traceable to primary standards. CMI will provide a calibrated standard detector and amplifier for use in the characterisation. | PTB, CMI, FAU, UdS | 24 | 32 | 1 | 1.1 | Scheduled for May 2020 (M24). A1.1.6 will be delayed by 8 2 months to January July 2020 (M32M26). | 6 | 2018-11-01
A1.1.7 | PTB will develop and characterise a complete standard single‑photon source that will comprise a GeV centre in bulk diamond with and without a planar antenna structure provided by UdS and FAU (A1.1.1 and A1.1.4). The complete source will be characterised in terms of its photon flux, its single photon purity (g(2)(0)‑value), its spectral characteristics (e.g. number of photons per wavelength) and its stability using reference standards (i.e. calibrated spectrometers and calibrated photodetectors) that are traceable to primary standards. CMI will provide a calibrated standard detector and amplifier for use in the characterisation. | PTB, CMI, FAU, UdS | 24 | 32 | 1 | 1.1 | Scheduled for May 2020 (M24). A1.1.7 will be delayed by 8 2 months to January July 2020 (M32M26). | 7 | 2018-12-01
A1.1.8 | Using input from A1.1.6 and A1.1.7, PTB, UdS, FAU and CMI will write a validation report, with a statement of uncertainty, summarising the results of the realisation of a traceable quantum standard single‑photon source based on optically and electrically‑driven SiV and GeV impurity centres in nano‑ and bulk diamonds in the visible wavelength range having, simultaneously, photon rates > 1 × 106 photons per second, emission bandwidths < 2 nm and high purity emission indicated by g(2)(t = 0) values < 0.05. Once agreed by the consortium, the coordinator will then submit the validation report to EURAMET as D1: ‘Validation report, with a statement of uncertainty, summarising the results of the realisation of a traceable quantum standard single‑photon source based on optically and electrically‑driven SiV and GeV impurity centres in nano‑ and bulk diamonds in the visible wavelength range having, simultaneously, photon rates > 1 × 106 photons per second, emission bandwidths < 2 nm and high purity emission indicated by g(2)(t = 0) values < 0.05’. | PTB, UdS, FAU, CMI | 28 | 34 | 1 | 1.1 | A1.1.8 will be delayed by 6 2 months to March 2021 September 2020 (M34M28). | 8 | 2019-01-01
A1.1.9 | Using the structures from A1.1.6 and A1.1.7, PTB will measure the collection efficiency and angular emission (back focal planning) of single SiV and GeV centres with and without a planar antenna structure. | PTB | 28 | 36 | 1 | 1.1 | A1.1.9 will be delayed by 8 2 months to May 2021 November 2020 (M36M30). | 9 | 2019-02-01
A1.1.10 | VTT will develop a customised optical excitation scheme for SiV-based SPS‑s for use in A1.1.6 (SiV will be used as the excitation sources are better understood). The device, realised in this activity, will have a stable and repeatable pulse energy. The optical excitation will have an adjustable repetition rate in the range from 10 kHz up to 100 MHz. | VTT | 18 | 30 | 1 | 1.1 | Delayed by 12 Months to November 2020 (M30) | 10 | 2019-03-01
A1.1.11 | Using input from A1.1.10, VTT and CMI will develop the control and monitoring software (LabView) that will be needed for the optical excitation scheme that was developed in A1.1.10. | VTT, CMI | 20 | 30 | 1 | 1.1 | Delayed by 12 Months to November 2020 (M30) | 11 | 2019-04-01
A1.2.1 | TUB will use existing methods to perform the epitaxial growth of at least 5 high quality AlGaAs/GaAs heterostructures with a single low density (< 109 cm-2) layer of InGaAs quantum dots (QD) in the active region of the semiconductor. The epitaxial growth will be based on at least 3 new, and 2 existing, numerically optimised device designs for maximum photon extraction efficiency of the quantum dot microlenses. The target emission wavelength is 930 nm. | TUB | 12 | 12 | 1 | 1.2 | Completed. | 12 | 2019-05-01
A1.2.2 | TUB will fabricate one deterministic quantum dot microlens per QD using in situ electron beam lithography. The processing will be based on the structures developed and grown in A1.2.1. Target values are an emission wavelength of 930 nm, emission linewidths of < 50 µeV, a photon extraction efficiency of > 50 % and g(2)(0) values of <~ 1 %. To maximise the extraction efficiency of the QD microlenses, TUB will explore the use of circular Bragg gratings to minimise the lateral losses of the QD microlenses. Additionally, TUB will develop QD microlenses attached to piezo actuators with a flip chip process that will enable the strain control of the QD’s spectral properties (e.g. the emission energy and the biexciton binding energy). | TUB | 24 | 30 | 1 | 1.2 | In principle completed. November 2020 (M30) | 13 | 2019-06-01
A1.2.3 | USTUTT will carry out the epitaxial deposition of single InGaAs quantum dots on a metamorphic InGaAs buffer layer on GaAs for an emission wavelength of 1550 nm. The buffer layer will be controlled so that the quantum dots can be precisely placed into photonic structures (e.g. the Bragg reflector semiconductor lens combination or the 2D photonic crystal, fabricated in this activity) that will maximise the emission properties. The dots currently have linewidths lower than 59 μeV and very high single‑photon purity. | USTUTT | 18 | 18 | 1 | 1.2 | Completed. | 14 | 2019-07-01
A1.2.4 | Using the structures deposited in A1.2.3, USTUTT will apply a newly developed in‑situ technique, with their optical in-situ lithography set-up, at 1550 nm to deterministically place quantum dots into the fabricated device structures, mentioned in A1.2.3, with the highest possible accuracy. | USTUTT | 24 | 30 | 1 | 1.2 | Delayed by 6 months to November 2020 (M30) | 15 | 2019-08-01
A1.2.5 | PTB, in collaboration with NPL, will develop and characterise two complete single‑photon setups, comprising the apparatus and single InGaAs quantum dot sources provided by TUB and USTUTT (A1.2.2 and A1.2.4), for emission wavelengths of 930 nm and 1550 nm. The characterisation will include measuring its photon flux, the single photon purity (g(2)(0)‑value) and the spectral characteristics (e.g. number of photons per wavelength). This will be performed using reference standards (i.e. calibrated spectrometers and calibrated photodetectors) that are traceable to primary standards. | PTB, NPL, TUB, USTUTT | 24 | 34 | 1 | 1.2 | 930 nm device (partly achieved): M24 -> M30 1550 nm device: M28 -> M34 | 16 | 2019-09-01
A1.2.6 | Using input from A1.2.5, PTB, TUB, USTUTT and NPL will write a validation report, with a statement of uncertainty, summarising the results of the realisation of traceable standard single‑photon sources based on InGaAs quantum dots emitting in the near‑infrared or telecom wavelength ranges having, simultaneously, photon rates > 1 × 106 photons per second, emission bandwidths < 2 nm and high purity emission indicated by g(2)(t = 0) values < 0.05. Once agreed by the consortium, the coordinator will then submit the validation report to EURAMET as D2: ‘Validation report, with a statement of uncertainty, summarising the results of the realisation of traceable standard single‑photon sources based on InGaAs quantum dots emitting in the near‑infrared or telecom wavelength ranges having, simultaneously, photon rates > 1 × 106 photons per second, emission bandwidths < 2 nm and high purity emission indicated by g(2)(t = 0) values < 0.05’. | PTB, TUB, USTUTT, NPL | 28 | 36 | 1 | 1.2 | Shift to M36 (May 2021) M30. | 17 | 2019-10-01
A1.2.7 | CMI will provide theoretical insight into the physics of the QD systems that were realised and experimentally investigated by TUB, NPL, USTUTT and PTB in A1.2.1 ‑ A1.2.5. CMI will use k.p perturbation theory to calculate single‑particle states followed by multi‑particle calculations that use the full configuration interaction method. Particular focus will be devoted towards computations of the fine‑structure splitting energy (FSS) of the ground state electron‑hole pair and its polarisation properties, both of which are essential for generating entangled photon pairs. The model for the calculations mentioned above, i.e. for calculating the energy levels of the QD in a specific structure, will employ realistic structural properties of QDs (i.e. shape, size, elastic strain) and it will also allow for the external tuning of fine structure splitting by electric, magnetic, or stress fields. Overall, the calculations will help with the design of the QD structures that will be fabricated in Task 1.2 and this will help with the interpretation of the measurements performed on those samples (e.g. optical, electrical, AFM). | CMI | 24 | 24 | 1 | 1.2 | Completed. | 18 | 2019-11-01
A1.3.1 | PTB, in collaboration with CNR, will define the optical (design) parameters (e.g. number of photons per wavelength) required to achieve a standard single‑photon source using a single molecule (determined in A1.3.2) as the emitter at cryogenic temperature (» 3 K). | PTB, CNR | 4 | 4 | 1 | 1.3 | Completed. | 19 | 2019-12-01
A1.3.2 | CNR will design and fabricate at least 3 single photon emitters, that are each based on a single molecule, that fulfil the design parameters provided in A1.3.1 for realising a standard single‑photon source. The devices will contain a hybrid multilayer planar antenna structure to optimise the collection efficiency of the single molecule emission at cryogenic temperature (» 3 K). CNR will characterise its emission rate, fluorescence, spectrum, single‑photon purity (g(2)(0)‑value), radiation pattern and collection efficiency. | CNR | 6 | 6 | 1 | 1.3 | Completed. | 20 | 2020-01-01
A1.3.3 | CNR will provide the device developed in A1.3.2 to PTB who will characterise it for its photon flux, single photon purity (g(2)(0)‑value), spectral characteristic (bandwidth) and stability by using reference standards (i.e. calibrated spectrometers and calibrated photodetectors) that are traceable to primary standards. Additionally, PTB will evaluate the capability of this device for use as a standard single‑photon emitter by analysing the results of the characterisation and by comparison with at least 2 other types of single photon sources from A1.1.6, A1.1.7, A1.2.5 and from the literature. | PTB, CNR | 26 | 26 | 1 | 1.3 | Completed. However still improvements under way. Measurement with pulsed excitation planned. See AP. Measurements were carried out at CNR. Sample for T = 10 K to PTB? See AP | 21 | 2020-02-01
A1.4.1 | INFN, INRIM and UNITO will create novel optically active colour centres in artificial diamond (< 1 mm3). INFN will implant at least 3 energetic ions of each of Sn, Pb, He, F, Cl and Er, in separate bulk diamonds (i.e. at least 18 diamonds in total), using their dedicated accelerator facilities. UNITO will optimise and use post‑implantation processing protocols (annealing, purification etc.) to ensure the formation of these desired defect complexes. INRIM, in collaboration with UNITO, will perform spectral, temporal and single‑photon emission (g(2)(t) measurement) characterisations to ensure a narrow emission bandwidth (< 2 nm), and a high emission rate (> 1 x 106 photons/s), with strong non‑classical emission, i.e. visibility > 85 %. | INFN, INRIM, UNITO | 24 | 30 | 1 | 1.4 | In principle completed, publication under way. Shift to M30 (November 2020). '• The following ion implantations were performed by INFN in IIa diamond bulk crystals: - 60 keV Sn- at 2 x 1010, 1 x 1011, 3 x 1011, 6 - 1011, 1 x 1012 cm-2 fluences, - 20 keV Pb- at 5 x 109, 1 x 1010, 4 x 1010 cm-2 fluences, - 35 keV PbO2- at 5 x 1012, 2 x 1013 cm-2 fluences, - 1.8 MeV He at 5 x 1010, 5 x 1011, 5 x 1012 cm-2 fluences, - 40 keV F- at 5 x 109, 1 x 1010, 4 x 1010 cm-2 fluence, - 3.6 MeV Cl3+ at 5 x 1010, 5 x 1011, 1 x 1013, 1 x 1014 cm-2 fluences, - 100 keV Er at 1 x 1013, 2 x 1013 cm-2 fluences. • Implantations were followed by specific thermal annealing, chemical treatment and surface oxygen plasma cleaning performed by UNITO. • The implanted diamond substrates were characterised in their ensemble spectral emission under 405 nm, 488 nm, 520 nm, and 532 nm at INRIM laboratories by INRiM, INFN, and UNITO. The room-temperature spectral characterisation led to the assessment of the formation of He- (535 nm and 560 nm emission lines), Sn- (zero-photon on line at 621 nm), Pb- (emission lines at 538 nm and 552 nm), and F-related (emission band in the 600 nm 800 nm spectral range) optical centres. No photoluminescence in the visible range associated with Cl and Er implantations was observed. • Sn, Pb-related centres were demonstrated at the single-photon emitter level at room temperature under 520 nm and 532 nm laser excitation. The SnV centre exhibited g2(0) values up to 0.29 ± 0.02 at 80 µW laser excitation, with a saturation luminescence intensity of 1.37 ± 0.01 x 106 photons/s under 1.11 ± 0.01 saturation power. The PbV centre exhibited a g2(0) value below 0.5 after background noise correction, which originated from first and second-order Raman scattering of diamond. A paper (Open Access) has been published [ACS Photonics 5, 4864 (2018)]. • Preliminary experiments also indicated anti-bunching behaviour from F-related centres. A systematic investigation of such emitters is currently in progress and is expected to be finalized within the scheduled end date of the task. • An optical cryostat, equipped with a dedicated photoluminescence confocal microscopy setup, has been installed in the INRiM laboratories. The cryostat has enabled the characterization of Sn-, Pb, and F-related emitters ensembles in the 5-300K temperature range providing preliminary insight on the attribution of the emission lines of the novel centres reported so far and to assess their bandwidth. The activity is on going (likely delayed because of the CoVID-19 crisis) — Preliminary experiments also indicated anti-bunching behaviour from F-related centres. A systematic investigation of such emitters has been carried at the ensemble level under different excitation wavelength to gain a further insight in their photo-physical properties. - An optical cryostat, equipped with a dedicated photoluminescence confocal microscopy setup, has been installed in the INRiM laboratories. The cryostat has enabled the characterisation of Sn-, Pb, and F-related emitters ensembles in the 5-300 K temperature range providing a deeper insight on the attribution of the emission lines of the novel centres reported so far and to assess their bandwidth. - Due to the COVID-19 outbreak, the Laboratories of INFN, UniTo and INRiM are currently closed until further notice. It is unlikely that further analyses of F-related center at the single-photon emitter level within month 24. Two research papers summarizing the results achieved on F-related ensemble emission and Pb-related quantum emitters are therefore currently in preparation and will be submitted for publication on an international peer-reviewed scientific journals | 22 | 2020-03-01
A1.4.2 | UNITO, INFN and INRIM will use the samples from A1.4.1 to develop electrically stimulated single‑photon sources based on the integration of graphitic micro‑channels into at least 1 of each of the bulk diamond substrates (i.e. at least 6 samples in total). They will identify the most effective new colour centres, prepared in A1.4.1, which are suitable for electrical stimulation (e.g. He‑ and Sn‑ related defects are already promising candidates). UNITO will define a suitable ion beam lithographic process for use in the fabrication of the integrated devices with embedded graphitic micro‑channels, and, in collaboration with INFN, will be responsible for the realisation of the devices using INFN facilities (i.e. at least 4 samples in total). INRIM, in collaboration with UNITO, will perform spectral, temporal and single‑photon emission (g(2)(t) measurement) characterisations of all of the devices that reach this step. The electrically driven single‑photon emitting devices will have their performance compared with an optically driven single‑photon emitting device and the advantages and disadvantages of the electrically driven single‑photon emitting devices will be assessed. | UNITO, INFN, INRIM | 36 | 42 | 1 | 1.4 | Shift to M42 (November 2021). The activity has started. A preliminary investigation of F-related ensemble emission in diamond in cathodoluminescence regime has revealed the optical activity of such class of emitters under the afore-mentioned excitation scheme. This result provides a strong indication that F-related centers are active under electrical stimulation. The emission of such optical center will be therefore investigated in A1.4.2 based on the fabrication of optimal geometries of integrated superficial (metallic) and sub-superficial (graphitic) electrodes | 23 | 2020-04-01
A2.1.1 | NPL and PTB will investigate the optical, electronic and atomic characteristics of naturally‑occurring defects in 2D materials, such as hexagonal boron nitride (hBN) and transition-metal dichalcogenides (TMDCs) e.g. tungsten diseledine and disulphide, which exhibit single‑photon emission. At least 5 mechanically exfoliated and chemical vapour deposited (CVD) materials (hBN and TMDCs) will be mapped at room and low temperature by NPL using Raman and photoluminescence (PL) spectroscopy to identify luminescent defects. Their single‑photon nature will be assessed at PTB and NPL using Hanbury Brown and Twiss (HBT) interference. NPL will use state‑of‑the‑art UHV equipment for room‑ and low‑temperature (AFM) and scanning tunnelling microscopy (STM) to probe and determine the electronic and atomic structure of the single‑photon emitting defects. | NPL, PTB | 24 | 30 | 2 | 2.1 | Delayed to M30 | 24 | 2020-05-01
A2.1.2 | NPL will artificially create deterministic arrays of quantum emitters using focused ion beams on mechanically exfoliated and CVD 2D materials. Arrays of emitters, typically 100 μm x 100 μm, with 2 μm to 10 μm lateral spacing will be fabricated using Ga ions with energies, dwell times and ion currents that are appropriate for the material used and its thickness. Their optical, electronic and atomic properties will be assessed by NPL and PTB using the techniques described in A2.1.1. | NPL, PTB | 30 | 36 | 2 | 2.1 | Delayed to M36 | 25 | 2020-06-01
A2.1.3 | Using input from A2.1.2, NPL and PTB will write a validation report on 2D material based single‑photon sources summarising the measured g(2)(0) values (standard uncertainty £ 2.5 %) from the 2D materials studied in WP2 as a function of their measured electronic and atomic parameters. Once agreed by the consortium, the coordinator will then submit the validation report to EURAMET as D3: ‘Validation report on 2D material based single‑photon sources summarising the measured g(2)(0) values (standard uncertainty £ 2.5 %) from the 2D materials studied in WP2 as a function of their measured electronic and atomic parameters’. | NPL, PTB | 33 | 39 | 2 | 2.1 | Delayed to M39 | 26 | 2020-07-01
A2.2.1 | CNR will explore at least 2 different positioning techniques e.g. spin-coating and micro‑infiltration, initially based on post‑selection, as well as deterministic strategies e.g. a-posteriori nano-positioning and nano-structuring, that are currently under investigation. Waveguide‑coupled single‑photon sources will be characterised, (brightness (i.e. the number of photons), single‑photon purity (g(2)(t=0)) and spectral characteristics (e.g. number of photons per wavelength)), using a free‑space detection setup in order to determine the collection efficiency and purity from single molecule emission. | CNR | 18 | 27 | 2 | 2.2 | Completed. | 27 | 2020-08-01
A2.3.1 | TUB will perform resonant optical excitation of at least 1 of the quantum dot microlenses (emitting at 930 nm) developed and realised in A1.2.2. Non resonant (above band gap), wetting layer resonant, p shell resonant, and strict resonant (resonance fluorescence) excitation will be compared in order to evaluate the impact of the excitation scheme on multi photon suppression (g(2)(0) value) and on the degree of indistinguishability (Hong Ou Mandel visibility V) (i.e. the best single photon sources will show the highest purity). The experiments will be performed under pulsed excitation, with varying pulse separation, to explore the time scale of charge carrier induced spectral diffusion. Tests will continue until the performance of the devices has been optimised. | TUB | 24 | 30 | 2 | 2.3 | Delayed to M30 | 28 | 2020-09-01
A2.3.2 | TUB will perform two photon resonant excitation of at least 1 of the quantum dot microlenses (emitting at 930 nm) developed and realised in A1.2.2. Two photon resonant excitation will be used to coherently drive the biexciton exciton cascade of the quantum dots. TUB will also perform comparative measurements under non resonant excitation, in order to determine the impact and advantages of this excitation scheme on the degree of indistinguishability and on the entanglement fidelity of the emitted photon pairs. | TUB | 30 | 36 | 2 | 2.3 | Delayed to M36 | 29 | 2020-10-01
A2.3.3 | USTUTT will characterise the properties of at least 1 of the newly developed QDs emitting in the telecom C band (1550 nm) (A1.2.3) after deterministic fabrication steps (A1.2.4). Linewidth, coherence, photon purity and indistinguishability will be investigated under different pumping conditions to deeply understand the physical properties of the sources. The pumping schemes that will be implemented will be non‑resonant, quasi‑resonant and strict resonant pumping in both continuous wave (CW) and pulsed regime (i.e. generating on‑demand photons). | USTUTT | 30 | 30 | 2 | 2.3 |  | 30 | 2020-11-01
A2.3.4 | USTUTT will extend the two‑photon excitation scheme which they first demonstrated in 2014. This will initially be used in the NIR (750 nm ‑ 1400 nm) and then it will be extended to the telecom wavelength (1550 nm) and suitable photonic structures will be deterministically implemented for this purpose. | USTUTT | 24 | 24 | 2 | 2.3 | Completed. | 31 | 2020-12-01
A2.3.5 | CSIC will design at least 2 monolithic devices (i.e. electrically‑driven single‑photon sources) which can simultaneously drive and tune the emission of single photons from quantum light sources by electrical means. The devices will comprise GaAs based quantum dots and wells (InAs and InGaAs typically) stacked on p-i-n-i-p or n-i-p-i-n layered structures. CSIC will test different configurations through Finite Difference Time Domain (FDTD), transfer matrix and self‑consistent Schrödinger‑Poisson solver methods to optimise their electrical and optical performance. The design will ensure that the monolithic source will be able to emit quantum light when connected to a power supply without the intervention of other light sources. | CSIC | 3 | 3 | 2 | 2.3 | Completed. | 32 | 2021-01-01
A2.3.6 | CSIC will monolithically fabricate at least 5 of the devices designed in A2.3.5 on semiconductor substrates. The fabrication will combine solid‑source epitaxial molecular beam epitaxy and microfabrication techniques like UV lithography, electron beam lithography, reactive ion etching. Room temperature photoluminescence and current/voltage (I/V) properties will be determined and compared with those specified in the design. | CSIC | 18 | 18 | 2 | 2.3 | Completed. | 33 | 2021-02-01
A2.3.7 | CSIC, in collaboration with TUB, will measure the performance of the ~5 devices from A2.3.6 at single‑photon level using micro photoluminescence spectroscopy, micro time‑resolved photoluminescence spectroscopy, HBT interferometry and HOM interferometry. The target is to demonstrate a prototype for single‑photon emission at around 950 nm and at T < 10 K. | CSIC, TUB | 24 | 30 | 2 | 2.3 | Delayed to M30 | 34 | 2021-03-01
A2.3.8 | CSIC, in collaboration with TUB, NPL and PTB, will explore the following device integration concepts: fibre coupling packaging and integration with photonic waveguide circuits and microlenses. | CSIC, TUB, NPL, PTB | 30 | 36 | 2 | 2.3 | Delayed to M36 | 35 | 2021-04-01
A2.3.9 | A metrological assessment of the performance of the excitation schemes developed in A2.3.1 ‑ A2.3.8 will be undertaken, using samples from A2.3.1 ‑ A2.3.8. NPL will perform measurements of g(2)(0) and indistinguishability. TUB, USTUTT and CSIC will provide information on the required optical and electrical excitation parameters, and will help to analyse any differences in the measurement results. | NPL, CSIC, TUB, USTUTT | 33 | 39 | 2 | 2.3 | Delayed to M39 | 36 | 2021-05-01
A2.3.10 | Using input from A2.2.1, CNR will write the first part of the validation report summarising the results of single‑molecule integration in dielectric waveguides: materials, geometries, relative coupling efficiency and g(2)(0) and summarising the measured g(2)(0) and indistinguishability (standard uncertainty £ 2.5 %) of single‑photon emission from the sources developed in Task 2.3, as a function of the excitation scheme and wavelength(s).Using input from A2.3.9, NPL, CSIC, TUB and USTUTT will write the second part of the validation report summarising the results of single‑molecule integration in dielectric waveguides: materials, geometries, relative coupling efficiency and g(2)(0) and summarising the measured g(2)(0) and indistinguishability (standard uncertainty £ 2.5 %) of single‑photon emission from the sources developed in Task 2.3, as a function of the excitation scheme and wavelength(s).Once agreed by the consortium, the coordinator will then submit the validation reports to EURAMET as D4: ‘Validation report summarising the results of single‑molecule integration in dielectric waveguides: materials, geometries, relative coupling efficiency and g(2)(0) and summarising the measured g(2)(0) and indistinguishability (standard uncertainty £ 2.5 %) of single‑photon emission from the sources developed in Task 2.3, as a function of the excitation scheme and wavelength(s)’. | NPL, CNR, CSIC, TUB, USTUTT | 34 | 40 | 2 | 2.3 | Delayed to M40 | 37 | 2021-06-01
A3.1.1 | TUB will create a fibre coupled single photon source. The source will be based on a single quantum dot that is deterministically integrated into a microlens with a backside distributed Bragg reflector or Au mirror. The QD microlens will be directly fibre coupled using an established gluing technique and on chip micro optics will be used to enhance the photon extraction efficiency. The source will be operated at 4.2 K by immersion into liquid helium. The device will be tested by TUB to see if it meets the target single photon emission rate of > 1 MHz at g(2)(0) < 0.1 and photon indistinguishability in excess of 90 %. | TUB | 30 | 36 | 3 | 3.1 | Delayed to M36 | 38 | 2021-07-01
A3.1.2 | TUB will explore the emission of polarisation entangled photon pairs from at least 1 of the deterministic quantum dot microlenses developed in A1.2.2. A fast, superconducting nanowire single photon detector (SNSPD) will be used to study the impact of finite fine structure splitting on the concurrence and negativity by means of quantum state tomography. This will include temperature dependent quantum state tomography which will be used to explore the influence of phonon induced spin flip processes on the entanglement fidelity. | TUB | 32 | 38 | 3 | 3.1 | Delayed to M38 | 39 | 2021-08-01
A3.1.3 | Using input from A3.1.2, INRIM, UNITO and TUB will write a report on single photon sources of indistinguishable and entangled photons based on near infrared (< 1 µm) quantum dot single‑photon sources with a visibility > 90 % for novel sensing and quantum measurements: advantages and limitations of the investigated sources. Once agreed by the consortium, the coordinator will then submit the report to EURAMET as D6: ‘Report on single photon sources of indistinguishable and entangled photons based on near infrared (< 1 µm) quantum dot single‑photon sources with a visibility > 90 % for novel sensing and quantum measurements: advantages and limitations of the investigated sources’. | INRIM, UNITO, TUB | 36 | 42 | 3 | 3.1 | The activity is not yet started. | 40 | 2021-09-01
A3.1.4 | CNR will optimise and characterise at least 1 of the planar antennas, which were developed for single molecule emission, in A1.3.1, as a source of indistinguishable photons. A double‑mirror configuration will both promote the zero‑phonon line (ZPL), with respect to other emission channels, as well as funnelling the emission around the normal axis. This device is expected to show a 65 % collection efficiency out of the cryostat window and a brightness for indistinguishable photons above 20 %. Indistinguishability will be evaluated with a HOM experiment for successive photons from the same source, as a function of the delay. | CNR | 18 | 30 | 3 | 3.1 | A3.1.4 is delayed by 12 6 months to November May 2020 (M30M24), this does not affect other activities. | 41 | 2021-10-01
A3.1.5 | USTUTT and TUB will characterise at least 2 samples, from A1.2.1 and A1.2.3, via at least 2 low temperature setups at NIR (750 nm – 1400 nm) and the telecom wavelength (1550 nm) as well as investigating the effect of at least 2 different pumping schemes on the photon properties, like indistinguishability and entanglement. Particular attention will be paid to using the two‑photon excitation technique, which has been pioneered by USTUTT for semiconductor QDs. This pumping scheme will allow for the generation of entangled photon pairs with improved indistinguishability. | USTUTT, TUB | 30 | 36 | 3 | 3.1 | Delayed to M36 | 42 | 2021-11-01
A3.2.1 | INRIM and UNITO will develop and optimise advanced sensing protocols based on the optical detection of magnetic spin resonances (ODMR) in colour centres in diamond with the aim of achieving an unprecedented level of sensitivity and spatial resolution (specifically, being able to reach the diffraction limit) in the mapping of electrical (e.g. in integrated electronics devices) or magnetic (e.g. in biological systems) fields. This activity will be based on the well‑established spin properties of the N‑V complex in diamonds. | INRIM, UNITO | 32 | 38 | 3 | 3.2 | Activity is almost completed. INRIM-UNITO-INFN unit has developed ODMR sensing protocols with NV centers showing 40 nT/Hz^1/2 magnetic sensitivity in continuous excitation. This is in line with the state of the art for the investigated sensing volume. Pulsed excitatition is underway and further improvement of sensitivity is expected. Furthermore, a novel technique for temperature sensing (with possible application in biological samples) has been developed. This technique has the advantage of being resilient to magnetic noise and the achieved sensitivity is 5 mK/Hz^1/2 (paper submitted). Also in this case the improvements are expected in the application of pulsed excitation.
A3.2.2 | UNITO, INRIM and INFN will attempt to find alternatives to N‑V defects which would be better sensors of electro‑magnetic fields. The new colour centres, explored in A1.4.1 (all samples) will be characterised using the ODMR measurement procedures developed in A3.2.1 in order to assess their spin properties. | UNITO, INRIM, INFN | 34 | 40 | 3 | 3.2 | The activity is on schedule. In order to find an alternative to NV defects in quantum-enhanced sensing applications, INFN employed ion implantation to produce the samples to be characterised with the ODMR protocols developed in A3.2.1, in order to assess their spin properties. It has become evident that ODMR measurements at cryogenic temperatures need to be performed to this scope, to allow for higher spin coherence times in the investigated defects. Therefore, UNITO and INRIM have established a new state-of-the-art experimental setup for the implementation of single-photon confocal photoluminescence and ODMR measurements down to 4 K temperature, based on a recirculating helium cryostat equipped with suitable optical windows. The system has been acquired and is now operational in its cryogenic functionalities, as well as in the acquisition of photoluminescence spectra from ensembles of optically active centres. A systematic investigation of the ODMR features of a specific class of new optically active defects (namely, He-related centers) started on month 20, which led to the identification of promising features in their spin resonance properties, which are yet to be fully deconvoluted from possible instrumental artifacts; this experimental activity was stopped during month 22 due to the covid-19 contingency. Furthermore, UNITO started the tender procedures for the acquisition a state-of-the-art multi-elemental ion implanter for the engineering of novel colour centres in diamond: such procedures are proceeding as planned, therefore (compatibly with the evolution of the covid-19 contingency plans) this new experimental facility is expected to be operational by the end of 2020.
A3.2.3 | INRIM will investigate the use of the genetic quantum measurement paradigm for the characterisation of single‑photon sources based on quantum dots and colour centres in diamond in collaboration with TUB and UNITO. Preliminary experiments will be designed and implemented in one of the three labs involved. | INRIM, UNITO, TUB | 24 | 24 | 3 | 3.2 | Completed. INRIM, in collaboration with UNITO and TUB have investigated the new paradigm dubbed the genetic quantum measurement. Specifically, they have investigated the possibility to exploit the genetic quantum measurement approach with quantum dots and colour centres in diamond, to understand if there is some peculiar observable of these quantum systems that can take advantage of this novel technique. Unfortunately, it was not identified any useful observable rather than the polarisation degree of freedom. Specifically, it is evident that the most suitable source for this degree of freedom is the heralded single-photon source, since it naturally emits photons in a defined linearly polarized state. Thus, INRIM exploited such a source to carry on the experiment in different regimes in terms of interaction strengths and polarization state. The experiment was carried on successfully in the INRIM labs with a HSPS in different regimes in terms of interaction strength and polarization state.
A3.2.4 | Using also input from A3.2.3, INRIM, UNITO and TUB will write a paper on genetic quantum measurement: a novel measurement approach. Once agreed by the consortium, the coordinator will then submit the paper to EURAMET as D5: ‘Paper on genetic quantum measurement: a novel measurement approach’. | INRIM, UNITO, TUB | 25 | 25 | 3 | 3.2 | Completed. On Going. A first draft is ready for the distribution. It is expected that the final version for the pubblication will be substantially different from the actual one.
A3.2.5 | CNR, in collaboration with INRIM, will work on the implementation of experimental schemes to provide sources of entangled photons based on single quantum emitters. CNR will use the source developed in A3.1.4, to try to generate a cluster state based on Mach‑Zehnder‑like schemes which will allow interference among successive photons from the same SPS. | CNR, INRIM | 30 | 36 | 3 | 3.2 | not yet started
A4.1.1 | CMI will develop low noise readout electronics (NEP ~ 20 fW.Hz-1/2) for the cooled PQED detector developed by Aalto. The electronics will be based on the switched integrator principle and will operate with biased photodiodes. Aalto will design, construct and characterise a cooled PQED in a liquid nitrogen operated cryostat for use in performing SI traceable measurements of single photon sources in WP4. The device, using the electronics developed above, will be capable of detecting 1 000 000 photons/s with an uncertainty of < 1 % in the wavelength range between 650 nm and 750 nm. | Aalto, CMI | 12 | 12 | 4 | 4.1 | Completed.
A4.1.2 | Metrosert, with support from CMI and Aalto, will implement a testbed which will be able to provide collinear input and output beams to better than ± 0.5 ºC of the transmission type detectors that use a slightly cooled (12 ºC) transmission type detector in conjunction with high accuracy readout electronics in the wavelength range from 650 nm to 750 nm consisting of small area commercial photodiodes (e.g. S1227 33BR from Hamamatsu). | Metrosert, Aalto, CMI | 18 | 30 | 4 | 4.1 | A4.1.2 delayed by 12 6 months to November May 2020 (M30M24).
A4.1.3 | Aalto and Metrosert will characterise the detector developed in A4.1.2 for its responsivity in the wavelength range from 650 nm to 750 nm and they will evaluate its performance against a conventional 6‑element transmission trap detector (available from the EMRP JRP EXL02 SIQUTE) and the PQED from A4.1.1. | Aalto, Metrosert | 24 | 36 | 4 | 4.1 | A4.1.3 is delayed by 12 6 months to May 2021 November 2020 (M36M30).
A4.1.4 | NPL will model and design two new absorber structures, involving modification of the superconducting thin film critical temperature (Tc) by different methods (e.g. co‑sputtered doping and variable thickness), of an inductive superconducting transition edge detector (ISTED) for operation at visible and telecoms wavelengths. INRIM will provide expertise on the design of the fibre‑coupling for the device. | NPL, INRIM | 18 | 18 | 4 | 4.1 | Completed.
A4.1.5 | NPL will characterise the photon‑number‑resolution depth and recovery time, at a visible and telecoms wavelength, of the prototype ISTED device developed in A4.1.4 operating at a temperature above 4.2 K. INRIM will use its expertise in characterising photon‑number‑resolving detectors to specify the measurements required, and how the experimental data will be analysed. | NPL, INRIM | 30 | 36 | 4 | 4.1
A4.1.6 | Using input from A4.1.5, NPL and INRIM will write a paper on the design and characterisation of the detection efficiency, photon‑number‑resolving depth and recovery time of the ISTED device. Once agreed by the consortium, the coordinator will then submit the paper to EURAMET as D7: ‘Paper on the design and characterisation of the detection efficiency, photon‑number‑resolving depth and recovery time of the ISTED device’. | NPL, INRIM | 33 | 39 | 4 | 4.1
A4.2.1 | FAU and PTB will design and construct a small portable confocal microscopy setup for single emitter measurements (targeted footprint size: about 50 cm x 30 cm). | FAU, PTB | 9 | 9 | 4 | 4.2 | Completed.
A4.2.2 | FAU and PTB will prepare at least 1 high‑quality sample containing NV‑ or SiV‑centres in diamond (NV is known to work, SiV will be used if it works) using the methods described in A1.1.1. The supporting cover glass will have markers so that it is possible to find the same defect whenever needed. | FAU, PTB | 12 | 30 | 4 | 4.2 | A4.2.2 is delayed by 18 12 months to November May 2020 (M30M24).
A4.2.3 | FAU and PTB will explore the sample prepared in A4.2.2 to identify suitable single‑emitters for bright single‑photon sources. These emitters will be placed in the small portable confocal microscope (A4.2.1). The best single‑photon source identified in A4.2.2, based on their photon rate and single-photon purity, will be tested and gauged with the on‑board gauged single‑photon counter. | FAU, PTB | 18 | 30 | 4 | 4.2 | Activity A4.2.3 is delayed by 12 6 months to November May 2020 (M30M24).
A4.2.4 | PTB and FAU will gauge at least 2 existing single photon avalanche detectors using the portable single‑photon source developed in A4.2.3. | PTB, FAU | 24 | 30 | 4 | 4.2 | Delayed to M30
A4.2.5 | TUB will integrate the fibre‑coupled single‑photon source realised in A3.1.1 into a compact Stirling cryocooler in order to realise a user‑friendly and stand‑alone quantum light source. The expected parameters of the QD based source are a photon rate of 12 000 photons/s, a g(2)(0) < 0.1 at an operational temperature of 40 K. The device will be characterised in absolute numbers by PTB and NPL. | TUB, PTB, NPL | 30 | 36 | 4 | 4.2
A4.2.6 | VTT will characterise the SPS‑s laser pumping source developed in A1.1.10. Pulse energy and area stability, and the repeatability of the optical pulses at different repetition rates between 10 MHz and 70 MHz will be measured using a 45 GHz photodetector and a 20 GHz oscilloscope setup from EMRP JRP EXL02 SIQUTE. | VTT | 20 | 30 | 4 | 4.2 | Activity A4.2.6 is delayed by 10 2 months to November March 2020.
A4.2.7 | Aalto and VTT, in collaboration with PTB, CMI and NPL, will adjust the pumping frequency and measure the single photon flux of the source developed in A1.1.6 using the cooled (10 OC) PQED from A4.1.1 and will calibrate the single photon detector from A4.1.4 at 650 nm (if NV) or 750 nm (if SiV). | Aalto, CMI, NPL, PTB, VTT | 30 | 36 | 4 | 4.2
A4.2.8 | Using input from A4.2.7, PTB, Aalto, CMI, INRIM, Metrosert, NPL, VTT, FAU and INFN will write a paper on the measurement infrastructure for the metrological characterisation of single‑photon sources at European NMIs. Once agreed by the consortium, the coordinator will then submit the paper to EURAMET as D8: ‘Paper on the measurement infrastructure for the metrological characterisation of single‑photon sources at European NMIs’. | PTB, Aalto, CMI, INRIM, Metrosert, NPL, VTT, FAU, INFN | 33 | 39 | 4 | 4.2
A4.3.1 | INRIM, UNITO and INFN will define and investigate novel criteria, including resilience to Poissonian noise, for detecting non‑classical behaviour in the fluorescence emission of ensembles of single‑photon emitters. In particular, INFN and UNITO will develop at least 3 clusters of NV centres in diamond for use in these tests using the methods described in A1.4.1 (the methods will be available at the start of A1.4.1). | INRIM, UNITO, INFN | 16 | 16 | 4 | 4.3 | Completed.
A4.3.2 | INRIM, UNITO and INFN will explore if it is feasible to use the criteria studied in A4.3.1 for mode reconstruction. Mode reconstruction is a quantum tomographic technique that exploits non-classicality criteria based on Glauber higher order correlation functions. It is expected that the criteria investigated in A4.3.1 will be suitable for performing the same task. INRIM, UNITO and INFN will also take another approach by implementing the reconstruction using the two criteria together. | INRIM, UNITO, INFN | 20 | 20 | 4 | 4.3 | Completed. The feasibility of the mode reconstration exploiting the criteria investigated in A.4.3.1, together with the higher order Glauber correlation functions, has been demonstrated exploiting Montecarlo numerical simulations in practcally achievable experimental scenario. Future outlook: it is planned to use this method to analyse previously collected datasets and compare the results with more standard reconstruction techniques.
A4.3.3 | INRIM will coordinate a round-robin pilot comparison on the measurement of the g(2)(0) value using the portable single photon source developed by FAU in A4.2.3. Comparison participants: INRIM, PTB, NPL, FAU. | INRIM, FAU, NPL, PTB | 30 | 36 | 4 | 4.3 | Delayed to M36. Activity has started. Preliminary design of the round-robin has been carried on with PTB and FAU (who jointly realized the source in A4.3.2). Preliminary schedule for the round-robin has been decided accounting for the contingency plan due to COVID-19 crisis, that may delay this activity. In particular, it has been decided that the source will be measured in at least two sites (labs) and that one of the participants should be in both sites in order to test the reproducibility of the source. The source will be operated CWand wavelength is still under discussion. A first draft of the measurement protocol will be prepared by INRIM and distributed among partners by April 2020 .
A5.1.1 | Scientific board: The project will create a scientific board of at least 7 members from 4 organisations to include the scientific and user community, CCPR, EURAMET, and the European Telecommunications Standards Institute (ETSI), representing at least 2 European countries. The aim of the scientific board is to clarify the needs of the various interested parties and to feed these into the project. Interaction of the scientific board will be achieved via a central website (see below) and at least 1 teleconference will be held every year. Key people in the scientific and user community, CCPR, EURAMET, and the European Telecommunications Standards Institute (ETSI) will be contacted regarding membership of the scientific board. | PTB, all partners | 36 |  | 5 | 5.1
A5.1.2 | Project webpage: A project webpage will be created using CMI’s IT infrastructure with public access and a part restricted for partners only. The webpage will be regularly updated with information for partners such as project reports, papers published by the partners, project meetings. The part of the website with restricted access will be dedicated to exchange information and reports throughout the project. It will also include a digital archive of all presentations, reports and papers from the project. | CMI, all partners | 36 |  | 5 | 5.1
A5.1.3 | Conference contributions: The partners plan to present at least 25 oral presentations at the following relevant international conferences and workshops: Single Photon Workshop 2019 (Milano, Italy, 2019), The International Conference on New Developments and Applications in Optical Radiometry – NEWRAD 2020 (Boulder, USA, 2020), Single Photon Workshop 2021 (location to be decided, 2021), Quantum Conferences in memory of Carlo Novero – Quantum (Torino, Italy 2019, 2021). Further relevant conferences will be identified during the project. | PTB, all partners | 36 |  | 5 | 5.1
A5.1.4 | Co-organisation of workshops: The Single‑Photon Workshops in 2019 and in 2021 will be co-organised by NPL, PTB and INRIM, which are members of the scientific board of the workshop. | NPL, PTB, INRIM | 36 |  | 5 | 5.1
A5.1.5 | Peer‑reviewed publications: The partners will submit at least 11 papers in total to peer‑reviewed journals during the project. Target journals include Physical Review Letters, Physical Review A, Applied Physics, Optics Express, Applied Optics, Optica and Metrologia or any other similar. The authors of the peer reviewed papers will clearly acknowledge the financial support provided through the EMPIR as required by EURAMET. | PTB, all partners | 36 |  | 5 | 5.1
A5.1.6 | Dissemination to metrology and standardisation bodies: Information on the results of the project will be disseminated to CCPR (in particular e.g. CCPR WG‑SP and CCPR WG‑KC), to EURAMET TC‑PR and to ETSI (in particular the ETSI Industry Specification Group on quantum key distribution, ETSI ISG‑QKD) (see Annex1, table in Section B2.c). The representatives of the partners in the corresponding committee or working group will jointly ask the chairperson to include a point in the agenda to briefly present the outputs of the project related to the WG activities and ask for feedback from the committee/WG to help guide the evolution of the project. | CMI, all partners | 36 |  | 5 | 5.1
A5.1.7 | Best practice guide: A best‑practice guide will be created on the use of single‑photon sources as radiation standards. It will be freely available from the project website. The target audiences are ETSI, measurement laboratories and R&D laboratories. | CMI, all partners | 36 |  | 5 | 5.1
A5.1.8 | Popular coverage: To enable other interested parties beyond the quantum community to understand the results of the project at least 3 articles will be submitted to trade journals such as Physics World and Wired and there will also be knowledge transfer to academia and schools. | NPL, all partners | 36 |  | 5 | 5.1
A5.1.9 | Special sessions: Special sessions will be organised, for dissemination purposes, during international conferences, such as the Single‑Photon Workshop (2019, 2021) and NewRad (2020), that are held during the lifetime of the project. | INRIM, all partners | 36 |  | 5 | 5.1 | Special sessions have been organized at Quantum 2019 conference in Torino, May 2019 as well as at the Single-Photon Workshop 2019 in Milano, October 2019. A special session is planned for For the NewRad 2020, Quantum 2021 conferences.
A5.1.10 | Monitoring EU flagship activities: PTB with the help of all partners will monitor the activities within the European quantum technology flagship programmes. As metrology is not prominent in these programmes, this activity will enable the NMIs/DIs to anticipate the research that they may be required to provide support to the metrology community in future years. | PTB, all partners | 36 |  | 5 | 5.1
A5.2.1 | At least six 1 day – 2 week training visits will be organised. The training courses will be targeted at the partners and they will cover training on the use of standard single-photon sources and the fabrication and characterisation of single-photon devices. The target number of trainees is between 1 and 3 per visit. Identification of the venues and attendees will take place at the M9 (February 2019) and M18 (November 2019) project meetings. | NPL, all partners | 30 |  | 5 | 5.2
A5.2.2 | At least 2 videos for e-training (from training seminars, lectures and presentations) on single‑photon sources and their applications will be developed by CMI and all other partners and posted on the project website. | CMI, all partners | 36 |  | 5 | 5.2
A5.2.3 | A stakeholder workshop (1 day’s duration) on the use of single‑photon standard sources will be organised and held in M32 or M33 (January 2021 or February 2021) at the EURAMET TC PR meeting 2021. The workshop will be open to all European NMIs. The workshop will present the results achieved by the project but will allow time for discussion of the results with all the participating stakeholders. The target number of delegates is around 20-30. | PTB, all partners | 32 |  | 5 | 5.2
A5.3.1 | A strategy plan for the exploitation of the research related to this project will be created at the beginning of the project and updated at each project meeting as required. | Aalto, all partners | 30 |  | 5 | 5.3
A5.3.2 | An exploitation plan, for the intellectual property developed in this project, will be created at the beginning of the project and reviewed and updated at each project meeting as required. | Aalto, all partners | 30 |  | 5 | 5.3
A5.3.3 | Contract negotiations on the licensing of the intellectual property rights produced within this project will be started with potential manufacturers of the single‑photon sources as new quantum standards (WP1), of the single‑photon sources based on new materials and concepts (WP2), of the single‑photon emitters for the creation of indistinguishable and entangled photons (WP3) and of the measurement infrastructure required for the metrological characterisation of single‑photon sources (WP4). | Aalto, all partners | 36 |  | 5 | 5.3
A6.1.1 | The project will be managed by the coordinator from PTB, who will be supported by the project management board consisting of one representative from each partner; including the leaders of each work package. The members of the project management board will guide the project, attend the project meetings, organise the progress meetings at their local institutes and call additional meetings if needed to ensure the overall project’s success. | PTB, all partners | 36 |  | 6 | 6.1
A6.1.2 | The work package leaders will report on the on‑going progress to the coordinator by e‑mail and telephone conferences. | PTB, all partners | 36 |  | 6 | 6.1
A6.1.3 | The coordinator, with support from the partners, will manage the project’s risks to ensure timely and effective delivery of the scientific and technical objectives and deliverables. | PTB, all partners | 36 |  | 6 | 6.1
A6.1.4 | The consortium will ensure that any ethics issues identified (see Section D3) are addressed. | PTB, all partners | 36 |  | 6 | 6.1
A6.2.1 | The kick‑off meeting involving all partners will be held approximately one month after the start of the project, at PTB. | PTB, all partners | 2 |  | 6 | 6.2 | Completed.
A6.2.2 | There will be five formal project meetings. These meetings include the kick‑off, mid‑term (around M18, November 2019) and final meeting (around M36, May 2021). The meetings will be held prior to reporting. The meetings will review progress and will be used to ensure partners are clear as to their role for the next period. The location of the meetings will rotate among the partners. Where possible, meetings may be held as satellite meetings to important conferences or committee meetings. | PTB, all partners | 36 |  | 6 | 6.2
A6.2.3 | In addition, technical meetings of work package groups may be held whenever necessary, and will be arranged on an ad‑hoc basis. | PTB, all partners | 33 |  | 6 | 6.2
A6.3.1 | One month after the signature of the grant agreement a publishable summary and a data management plan (DMP) will be produced and submitted to EURAMET. | PTB, all partners | 2 |  | 6 | 6.3 | Completed.
A6.3.2 | Following Articles 17 and 20 of the grant agreement, information will be submitted to EURAMET, in accordance with the procedures issued by them to enable EURAMET to comply with its obligations to report on the programme to the European Commission. *Progress reports will be submitted at months 9, 27 (February 2019, August 2020 + 45 days), 18, 36 (November 2019, May 2021 + 60 days). * Impact/Output reports and data management plans (if applicable) will be submitted at the same times. All partners will provide input to these reports and the coordinator will provide these and updated publishable summaries to EURAMET. | PTB, all partners | 36 |  | 6 | 6.3
A6.3.3 | Periodic Reports (including financial reports and questionnaires) will be delivered at months 18 and 36 (November 2019, May 2021 + 60 days) in accordance with Article 20 of the grant agreement. All partners will provide input to these reports and the coordinator will provide these to EURAMET. | PTB, all partners | 36 |  | 6 | 6.3
A6.3.4 | Final Reports will be delivered at month 36 (May 2021 + 60 days) in accordance with Article 20 of the grant agreement. All partners will provide input to these reports and the coordinator will provide these to EURAMET. | PTB, all partners | 36 |  | 6 | 6.3